## Slide 1
Big Data Analytics – BDAT1003
Mary Lijo Cletus
Akshay Vijayan
Arshad Rafeek Shemi
Analytics Analyst
Project Code:GEO 1327
Replace with Client logo

## Slide 2: Project Summary
The project will be focused on Digital Marketing Analysts and will be responsible for analyzing data from insights and reports from Sharon Bonner Consulting social media platforms. We will review and analyze the current and projected marketing initiatives and provide suggestions. Analyze keywords to determine relevant search terms to the organization and ensure the Search Engine Optimization. And finally, to analyze the overall business and provide recommendations on the current strategies. The project objectives are:
1. Conduct analysis that results in actionable insights and data-driven recommendations.
2. Identify, communicate, and act on opportunities and risks proactively.
3. Report and present performance and recommendations.

## Slide 3: Team Profile
Team Lead
Akshay Vijayan
Team Member
Arshad Rafeek Shemi
Team Member
Mary Lijo Cletus
Developer
Business Analyst
Data Analyst
Data analysis and data visualization
Managing proper communication between client and the team,
Data analysis
Lead the group
Development and testing

## Slide 4: Communication Plan
Name | Role | Send/Receive Email | Weekly Meetings | Decisions | Documentation
Sharon Bonner | Stakeholder | Yes | Attend | Project Scope | Project documentation
Brunilda Xhafellari | Instructor | Yes | Optional Attendee | Progression of Project | Grading
Brunilda Xhafellari | Project Manager | Yes | Suggested Attendee | Project and Task Management related items | Project Management Presentation components
Akshay Vijayan | Team Lead | Yes | Attend, Book, Minutes, Agenda | Team, Project and Own Tasks | Communication
Arshad Rafeek Shemi | Team Member | Yes | Attend | Own Tasks | Documentation of different project phase
Mary Lijo Cletus | Team Member | Yes | Attend | Own Tasks | Documentation of different project phase

## Slide 5: High-Level Timeline Chart (GANTT)
The GANTT chart above shows the high-level tasks and expected dates for this project
Chart: 
| Requirements | Design | Development | Testing | Release
Start Date | 44746 | 44810 | 44830 | 44872 | 44886
Duration of Dates | 39 | 17 | 38 | 11 | 25

## Slide 6: High-Level Timeline Chart (GANTT)
Chart: 
| Requirements | Design | Development | Testing | Release
Start Date | 44746 | 44810 | 44830 | 44872 | 44886
Duration of Dates | 39 | 17 | 38 | 11 | 25

## Slide 7: Budget
Current Cost of Project
Task | Hours | Rate | Total
Akshay Vijayan | 4 | $ 50.00 | $ 200.00
Arshad Rafeek Shemi | 4 | $ 50.00 | $ 200.00
Mary Lijo Cletus | 4 | $ 50.00 | $ 200.00
Total |  |  | $ 600.00
Chart: Budget vs Actual
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | week11 | week12 | week13 | week14
Actual | 600 | 700 | 600 | 400 | 550 | 800 | 350 | 500 | 700 | 650 | 570 | 900 | 1000 | 1100
Budget | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000

## Slide 8: Project Progress Update
Summary of Current State
  Proper understanding about the deliverables and the project requirements
  Good communication between client and project members
Current tasks
  Research on collection of data
Upcoming Plans
  Collection of required data from client

## Slide 9: Plans for the next Weekly Status Report
This week we will mainly cover the issues related to data availability
Chart: 
| Research on useful datas to be collected | Conducting Client Meeting | Team meeting to discuss on next phase | Finding Different data sources for project
Start Date | 44774 | 44775 | 44776 | 44777
Duration of Dates | 6 | 0 | 0 | 3

## Slide 10: Individual Status Report – Akshay Vijayan
Research on coding and development required for project
Upcoming Plans
Finding meaningful data for analysis
Leading the team in proper path
Chart: Budget vs Actual
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | week11 | week12 | week13 | week14
Actual | 1 | 2 | 4 | 6 | 8
Budget | 8 | 8 | 8 | 8 | 8

## Slide 11: Individual Status Report – Mary Lijo Cletus
Research on data collection from client website
Upcoming Plans
1. Doing research on types of data for analysis
2. Preparation of minutes of meeting
Chart: Budget vs Actual
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | week11 | week12 | week13 | week14
Actual | 1 | 2 | 4 | 6 | 8
Budget | 8 | 8 | 8 | 8 | 8

## Slide 12: Individual Status Report – Arshad Rafeek Shemi
Maintaining proper communication between client and team
Research on finding data for analysis
Upcoming Plans
1. Doing research on types of data for analysis
2. Preparing for next meeting
Chart: Budget vs Actual
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | week11 | week12 | week13 | week14
Actual | 1 | 2 | 4 | 6 | 8
Budget | 8 | 8 | 8 | 8 | 8

## Slide 13: Questions and Answers
What in case client deny to give data that is needed for project or if they don’t have adequate data to provide the team?