## Slide 1
Big Data Analytics – BDAT1011
Mary Lijo Cletus
Akshay Vijayan
Arshad Rafeek Shemi
Analytics Analyst
Project Code:GEO 1327

## Slide 2: Project Summary
The project will be focused on Digital Marketing Analysts and will be responsible for analyzing data from insights and reports from Sharon Bonner Consulting social media platforms. We will review and analyze the current and projected marketing initiatives and provide suggestions. Analyze keywords to determine relevant search terms to the organization and ensure the Search Engine Optimization. And finally, to analyze the overall business and provide recommendations on the current strategies. The project objectives are:
1. Conduct analysis that results in actionable insights and data-driven recommendations.
2. Identify, communicate, and act on opportunities and risks proactively.
3. Report and present performance and recommendations.

## Slide 3: Team Profile
Akshay Vijayan
Arshad Rafeek Shemi
Mary Lijo Cletus
Developer
Business Analyst
Data Analyst
Data analysis and data visualization
Managing proper communication between client and the team,
Data analysis
Managing cleaning and developing solutions from data
Development and testing

## Slide 4
Project Objectives
• Conduct analysis that results in actionable insights and data-driven recommendations.
• Identify, communicate, and act on opportunities and risks proactively.
• Report and present performance and recommendations.
Project Requirements
• A strategy to make everyone understand the different between event consulting and event producing.
• A strategy to get clients for Sharon Bonner Consulting from the historical data of Bright Ideas event agency.
• Immediate actionable insights that can be implemented for the initial push for the company.
• A 3–5-year analytical strategy for the company to move forward with event consulting.

## Slide 5
Scope of Project
1) Analysis of data obtained from client or from other external sources that results in actionable insights and data-driven recommendations.
2) Report and present performance and recommendations.
3) Analytical strategy for 3–5-years prepared for the company to focus on event consulting industry.

## Slide 6
Project Outcomes
• Getting proper data driven recommendations in marketing of the company
• Getting to know about new opportunities and risks of event consulting industry
• Get a detailed analysis report of previous clients and data
• Get project deliverables which can be used for future research purposes.
Project Deliverables
1. A final report with data-driven suggestions and reflections on how to improve our business
2. A 3–5-year future analytical plan
3. Immediate actionable insights that we can implement

## Slide 7: Communication Plan
Name | Role | Send/Receive Email | Weekly Meetings | Decisions | Documentation
Sharon Bonner | Stakeholder | Yes | Attend | Project Scope | Project documentation
Thecla Oreme | Instructor | Yes | Optional Attendee | Progression of Project | Grading
Thecla Oreme | Project Manager | Yes | Suggested Attendee | Project and Task Management related items | Project Management Presentation components
Akshay Vijayan | Team Lead | Yes | Attend, Book | Team, Project and Own Tasks | Communication
Arshad Rafeek Shemi | Team Member | Yes | Attend, Agenda | Own Tasks | Documentation of different project phase
Mary Lijo Cletus | Team Member | Yes | Attend, Minutes | Own Tasks | Documentation of different project phase

## Slide 8: High-Level Timeline Chart (GANTT)
Chart: 
| Requirements | Design | Development | Testing | Release
Start Date | 44746 | 44810 | 44830 | 44872 | 44886
Duration of Dates | 39 | 17 | 38 | 11 | 25

## Slide 9: Budget
Current Cost of Project
Task | Hours | Rate | Total
Akshay Vijayan | 8 | $ 50.00 | $ 400.00
Arshad Rafeek Shemi | 8 | $ 50.00 | $ 400.00
Mary Lijo Cletus | 8 | $ 50.00 | $ 400.00
Total |  |  | $ 1200.00
Chart: Budget vs Actual
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | week11 | week12 | week13 | week14
Actual | 600 | 700 | 600 | 400 | 550 | 800 | 350 | 500 | 700 | 650 | 570 | 900 | 1000 | 1100
Budget | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
A total budget off $4800 per person ($400 x 12 weeks)

## Slide 10: Project Progress Update
Summary of Current State
  Analysis of Google Analytics for the client website
  Dashboard presentation of social media analysis
Current tasks
  Dashboard for google Analytics
Upcoming Plans
  Data mining from different similar companies as that of our client

## Slide 11: Activities in Progress
Preparing for the dashboard creation based on the Google Analytics Analysis done for the client website
Preparing for the Next client meeting
Learning new tools for the Data mining for the project

## Slide 12: Backlogs and Schedules
No backlogs so far
Next client meeting will be according to the client's availability

## Slide 13: Activities and Works so far
First Client meeting was done on 21/09/2022
Second Client meeting was done on 29/09/2022
Third Client meeting was done on 13/10/2022
Immediate recommendations on website provided for the client's website updation
Detailed analysis of the client social media
Dashboard preparation of client’s social media
Analysis of google analytics of client website

## Slide 14: Plan for Next week
Dashboard presentation based on the analysis on google analytics
Preparation for next client meeting

## Slide 15: Individual Status Report – Akshay Vijayan
Data collection and verification of google analytics data

## Slide 16: Individual Status Report – Mary Lijo Cletus
Verification and validation of google analytics data and its analysis

## Slide 17: Individual Status Report – Arshad Rafeek Shemi
Maintaining proper communication between client and team
Research on dashboard presentation for client’s google analytics data

## Slide 18: Conclusion
In this project we conduct analysis that results in actionable insights and data-driven recommendations. This is a great project for us to prove our analyzing expertise for future employers, as the impact of our work on this project can be easily measured and communicated. We here by thank the entire Georgian College faculty from Big Data Analytics program.