## Slide 1
Big Data Analytics – BDAT1011
Mary Lijo Cletus
Akshay Vijayan
Arshad Rafeek Shemi
Analytics Analyst
Project Code:GEO 1327

## Slide 2: Project Summary
The project will be focused on Digital Marketing Analysts and will be responsible for analyzing data from insights and reports from Sharon Bonner Consulting social media platforms. We will review and analyze the current and projected marketing initiatives and provide suggestions. Analyze keywords to determine relevant search terms to the organization and ensure the Search Engine Optimization. And finally, to analyze the overall business and provide recommendations on the current strategies.

## Slide 3: Team Profile
Akshay Vijayan
Arshad Rafeek Shemi
Mary Lijo Cletus
Developer
Business Analyst
Data Analyst
Data analysis and data visualization
Managing proper communication between client and the team,
Data analysis
Managing cleaning and developing solutions from data
Development and testing

## Slide 4
Project Objectives
• Conduct analysis that results in actionable insights and data-driven recommendations.
• Identify, communicate, and act on opportunities and risks proactively.
• Report and present performance and recommendations.
Project Requirements
• A strategy to make everyone understand the different between event consulting and event producing.
• A strategy to get clients for Sharon Bonner Consulting from the historical data of Bright Ideas event agency.
• Immediate actionable insights that can be implemented for the initial push for the company.
• A 3–5-year analytical strategy for the company to move forward with event consulting.

## Slide 5
Scope of Project
1) Analysis of data obtained from client or from other external sources that results in actionable insights and data-driven recommendations.
2) Report and present performance and recommendations.
3) Analytical strategy for 3–5-years prepared for the company to focus on event consulting industry.

## Slide 6
Project Outcomes
• Getting proper data driven recommendations in marketing of the company
• Getting to know about new opportunities and risks of event consulting industry
• Get a detailed analysis report of previous clients and data
• Get project deliverables which can be used for future research purposes.
Project Deliverables
1. A final report with data-driven suggestions and reflections on how to improve our business
2. A 3–5-year future analytical plan
3. Immediate actionable insights that we can implement

## Slide 7: Communication Plan
Name | Role | Send/Receive Email | Weekly Meetings | Decisions | Documentation
Sharon Bonner | Stakeholder | Yes | Attend | Project Scope | Project documentation
Thecla Oreme | Instructor | Yes | Optional Attendee | Progression of Project | Grading
Thecla Oreme | Project Manager | Yes | Suggested Attendee | Project and Task Management related items | Project Management Presentation components
Akshay Vijayan | Team Lead | Yes | Attend, Book | Team, Project and Own Tasks | Communication
Arshad Rafeek Shemi | Team Member | Yes | Attend, Agenda | Own Tasks | Documentation of different project phase
Mary Lijo Cletus | Team Member | Yes | Attend, Minutes | Own Tasks | Documentation of different project phase

## Slide 8: High-Level Timeline Chart (GANTT)
Chart: 
| Requirements | Design | Development | Testing | Release
Start Date | 44746 | 44810 | 44830 | 44872 | 44886
Duration of Dates | 39 | 17 | 38 | 11 | 25
High Level Time Line GANTT chart here represents our project timeline and the deadlines

## Slide 9: Budget
Current Cost of Project
Task | Hours | Rate | Total
Akshay Vijayan | 8 | $ 50.00 | $ 400.00
Arshad Rafeek Shemi | 8 | $ 50.00 | $ 400.00
Mary Lijo Cletus | 8 | $ 50.00 | $ 400.00
Total |  |  | $ 1200.00
Chart: Budget vs Actual
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | week11 | week12 | week13 | week14
Actual | 600 | 700 | 600 | 400 | 550 | 800 | 350 | 500 | 700 | 650 | 570 | 900 | 1000 | 1100
Budget | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
A total budget off $4800 per person ($400 x 12 weeks)

## Slide 10: Project Progress Update
Summary of Current State
  Analysis of Google Analytics for the client Social media Accounts
  Dashboard presentation of social media analysis
  Data Scrapping From different similar companies
  Word Cloud preparation for different links provided by the company
  Prepared reports for the website analysis done.
  Documentation works related to the works done so far
Current tasks
  Started designing the next 3 to 5 year plan
  Conducts Meetings and discussions for the 3 to 5 year plan

## Slide 11: Activities in Progress
Preparing for the Next client meeting
Analysis of 3 to 5 year plan

## Slide 12: Activities and Works so far
First Client meeting was done on 21/09/2022
Second Client meeting was done on 29/09/2022
Third Client meeting was done on 13/10/2022
Fourth Client meeting was done on 3/11/2022
Immediate recommendations on website provided for the client's website updation

## Slide 13
Detailed analysis of the client social media
Dashboard preparation of client’s social media
Analysis of google analytics of client website
Data is scrapped from similar companies and Word Cloud for SEO keywords was done.
Data is scrapped from the data sources provided by the client and Word Cloud for SEO keywords was done

## Slide 14: Plan for Next week
Preparation for next client meeting
Preparation for the next 3 to 5 year plan
Milestone | Start Date* | End Date*
Client Meeting | 24-11-2022 | 24-11-2022
Data Source Reserach | 24-11-2022 | 30-11-2022
Development | 25-11-2022 | 26-11-2022
Documentation | 25-11-2022 | 30-11-2022
Group Meeting | 28-11-2022 | 28-11-2022
Report Preparation | 27-11-2022 | 30-11-2022
Preparation of 3 to 5 year Plan | 24-11-2022 | 30-11-2022

## Slide 15: Individual Status Report – Akshay Vijayan
Research on the programming side and data collection to prepare the 3 to 5 year plan for the client
Chart: Budget vs Actual
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | week11 | week12 | week13 | week14
Actual | 1 | 2 | 4 | 6 | 8
Budget | 8 | 8 | 8 | 8 | 8

## Slide 16: Individual Status Report – Mary Lijo Cletus
Research on different data sources for making the 3 to 5 year plan
Chart: Budget vs Actual
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | week11 | week12 | week13 | week14
Actual | 1 | 2 | 4 | 6 | 8
Budget | 8 | 8 | 8 | 8 | 8

## Slide 17: Individual Status Report – Arshad Rafeek Shemi
Maintaining proper communication between client and team
Preparation of Document and reports for the analysis done so far
Prepared report for the clients website Analysis
Chart: Budget vs Actual
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | week11 | week12 | week13 | week14
Actual | 1 | 2 | 4 | 6 | 8
Budget | 8 | 8 | 8 | 8 | 8

## Slide 18: Backlogs and Schedules
No backlogs so far
Next client meeting will be on 24-11-2022

## Slide 19: Conclusion
In this project we conduct analysis that results in actionable insights and data-driven recommendations. This is a great project for us to prove our analyzing expertise for future employers, as the impact of our work on this project can be easily measured and communicated. We here by thank the entire Georgian College faculty from Big Data Analytics program.