## Slide 1
Big Data Analytics – BDAT1011
Mary Lijo Cletus
Akshay Vijayan
Arshad Rafeek Shemi
Analytics Analyst
Project Code:GEO 1327

## Slide 2: Project Summary
The project will be focused on Digital Marketing Analysis and will be responsible for analyzing data from insights and reports from Sharon Bonner Consulting company’s social media platforms. We will review and analyze the current and projected marketing initiatives and provide suggestions. Analyze keywords to determine relevant search terms to the organization and ensure the Search Engine Optimization. And finally, to analyze the overall business and provide recommendations on the current strategies.

## Slide 3: Team Profile
Akshay Vijayan
Arshad Rafeek Shemi
Mary Lijo Cletus
Developer
Business Analyst
Data Analyst
Data analysis and data visualization
Managing proper communication between client and the team,
Data analysis
Managing cleaning and developing solutions from data
Development and testing

## Slide 4
Project Objectives
• Conduct analysis that results in actionable insights and data-driven recommendations.
• Identify, communicate, and act on opportunities and risks proactively.
• Report and present performance and recommendations.
Project Requirements
• A strategy to make everyone understand the different between event consulting and event producing.
• A strategy to get clients for Sharon Bonner Consulting from the historical data of Bright Ideas event agency.
• Immediate actionable insights that can be implemented for the initial push for the company.
• A 3–5-year analytical strategy for the company to move forward with event consulting.

## Slide 5
Scope of Project
1) Analysis of data obtained from client or from other external sources that results in actionable insights and data-driven recommendations.
2) Report and present performance and recommendations.
3) Analytical strategy for 3–5-years prepared for the company to focus on event consulting industry.

## Slide 6
Project Outcomes
• Getting proper data driven recommendations in marketing of the company
• Getting to know about new opportunities and risks of event consulting industry
• Get a detailed analysis report of previous clients and data
• Get project deliverables which can be used for future research purposes.
Project Deliverables
1. A final report with data-driven suggestions and reflections on how to improve our business
2. A 3–5-year future analytical plan
3. Immediate actionable insights that we can implement

## Slide 7: Communication Plan
Name | Role | Send/Receive Email | Weekly Meetings | Decisions | Documentation
Sharon Bonner | Stakeholder | Yes | Attend | Project Scope | Project documentation
Thecla Oreme | Instructor | Yes | Optional Attendee | Progression of Project | Grading
Libin Koshy | Project Manager | Yes | Suggested Attendee | Project and Task Management related items | Project Management Presentation components
Akshay Vijayan | Team Lead | Yes | Attend, Book | Team, Project and Own Tasks | Communication
Arshad Rafeek Shemi | Team Member | Yes | Attend, Agenda | Own Tasks | Documentation of different project phase
Mary Lijo Cletus | Team Member | Yes | Attend, Minutes | Own Tasks | Documentation of different project phase

## Slide 8: High-Level Timeline Chart (GANTT)
Chart: 
| Requirements | Design | Development | Testing | Release
Start Date | 44746 | 44810 | 44830 | 44872 | 44886
Duration of Dates | 39 | 17 | 38 | 11 | 25
High Level Time Line GANTT chart here represents our project timeline and the deadlines

## Slide 9: Budget
Current Cost of Project
Task | Hours | Rate | Total
Akshay Vijayan | 8 | $ 50.00 | $ 400.00
Arshad Rafeek Shemi | 8 | $ 50.00 | $ 400.00
Mary Lijo Cletus | 8 | $ 50.00 | $ 400.00
Total |  |  | $ 1200.00
Chart: Budget vs Actual
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | week11 | week12 | week13 | week14
Actual | 600 | 700 | 600 | 400 | 550 | 800 | 350 | 500 | 700 | 650 | 570 | 900 | 1000 | 1100
Budget | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
A total budget off $4800 per person ($400 x 12 weeks)

## Slide 10: Project Progress Update
Summary of Current State
  Prepared the 1st year plan and 2nd Year plan for the client
  Analysis of Google Analytics for client's Social media Accounts
  Dashboard presentation for social media analysis
  Data Scrapping from client's competitor companies
  Word Cloud preparation for different links provided by the company
  Analyzed Clients Website and shared insights for updating the website
  Prepared reports for the website analysis done.
  Analyzed client's website after the updating the website, as requested by the client
  Documentation works related to the works done so far
  Current tasks
  Started designing the next 3rd year plan
  Conducts Meetings and discussions for preparing the 3rd year plan

## Slide 11: Activities –Last week
Prepared the 1st year plan and 2nd Year plan for the client
As part of the 3 to 5 year plan Our client has requested to split the 3-to-5-year plan to
1 year plan: Which includes the immediate actions that should be taken
2-year plan: Which includes the measures that should be taken in the 2nd year
3-year plan: Which includes the long-time plans that should be taken in the 3 year
Analyzed client website for the second time as part of their request to know the functioning after updating their website

## Slide 12: Activities and Works so far
Immediate recommendations and insights were shared with the client based on website the analysis of website. For updating their website.
As per the client request a re analysis is done for their website after updating their website.
Detailed analysis of the client’s social media accounts
Dashboard preparation of client’s social media

## Slide 13
Analysis of google analytics of client website
Data is scrapped from similar companies and Word Cloud for SEO keywords was done.
Data is scrapped from the data sources provided by the client and Word Cloud for SEO keywords was done

## Slide 14: Plan for Next week
Preparation for the next 3rd year plan
Milestone | Start Date* | End Date*
Data Source Research | 30-11-2022 | 30-11-2022
Development | 1-12-2022 | 2-12-2022
Documentation | 2-12-2022 | 6-12-2022
Group Meeting | 3-12-2022 | 4-12-2022
Report Preparation | 5-12-2022 | 6-12-2022
Preparation of 3rd year Plan | 30-12-2022 | 6-12-2022

## Slide 15: Backlogs and Schedules
No backlogs so far

## Slide 16: Conclusion
In this project we conduct analysis that results in actionable insights and data-driven recommendations. This is a great project for us to prove our analyzing expertise for future employers, as the impact of our work on this project can be easily measured and communicated. We here by thank the entire Georgian College faculty from Big Data Analytics program.